## Sheet1
POLY Strategic Plan 2018
VISION: Be the premier professional organization promoting polymer science and its value to society.
MISSION: Advance the broader polymer enterprise and its practitioners to meet the global challenges of today and the future.
Goals/Strategies/Tasks | Target Completion Date | Champion | Team Lead | Team Members | Responsible | Resources Needed | Task Completion Date | Comments
Goal 1: Grow a robust, diverse, and engaged global organization that encompasses the broader polymer enterprise. [Impact, H; Resources, H]
Strategy 1: By December 2018, create and provide a welcoming package to provide to new members within 1 month of joining. [Impact, H; Resources, M] Champion: Diana G | 2018-12-31 | Diana | Diana | Potential: Diana Gerbi, Kathy Mitchem, Toby Nelson. Potential: Kat Knauer, Laura Stratton
Task 1: Establish team and check with ACS video on costs, etc. |  |  |  |  | Diana |  | 2018-02-28
Task 2: Committee decides on new member welcome package content (video?) |  |  |  |  | Team | $ 2k for video | 2018-03-19 | ACS Developed a recruitment video for POLY. It is proposed that a new member video be considered and it is requested that deadline for this be updated to 12/31/2019. Should this point be combined with Strat 3.2?
Task 3: Implement Welcome Package |  |  |  |  | Kathy/Carlee |  | 4/31/18 | Diana provided letter, Carlee sends out 2x/yr
Task 4: Implement Chair letter for 1 yr new members (discount?) |  |  |  |  | Kathy/Carlee |  | 2018-06-30 | Diana provided letter, Carlee sends out 2x/yr
Task 5: If using ACS video-make at Fall Meeting |  |  |  |  | Diana/Others |  | 2018-08-19 | ACS developed a recruitment video for POLY in Fall 2018
Strategy 2: By Fall 2018 ACS meeting, develop a recruiting plan to increase membership by 2% per year over the next 3 years. [Impact, M; Resources, H] Champion: Kevin C | 2021-01-28 | Kevin Cavicchi | Kevin Cavicchi | POLY membership committee |  | $1k
Task 1: Data Analysis of Membership Data to determine a: where new members come from and where members are lost |  |  |  |  | Kevin Cavicchi |  | 2018-07-01 | Carlee submitted POLY speakers for free membership sent with welcome letter (Kevin)
Task 2: Recruiting Plan: National Meeting/ member-get-a-member/student chapters/reg. or local meetingRecruiting Plan: National Meeting/ member-get-a-member/student chapters/reg. or local meeting |  |  |  |  | POLY membership committee |  | 2018-08-19
Strategy 3: Work with international chapters to identify 2 ambassadors by fall 2018 to co-organize a workshop in Asian country or Pacific Rim by 2020. [Impact, H; Resources, M] Champion: Mike M. | 2020-12-31 | Mike Meador | TBD | Potential: 2 POLY ambassadors, POLY Office, POLY Leadership Rep, ACS Intl Chapter Members, POLY International Member, e.g., James Wang
Task 1: Establish working team/Team Lead by Fall Meeting |  |  |  |  | Mike Meador |  | 2018-08-19 | Discussion took place at the Fall Workshop Committee to share ideas. Mike Meador has been added to the POLY International Committee
Task 2: Get Int. Chapter Chair contact info from ACS HQ | [6 empty] | 2018-08-19
Task 3: Contact Int Chapter Chairs and POLY international members and identify co-chairs | [6 empty] | 2018-08-19
Task 4: Plan and conduct workshop | [6 empty] | 2020-12-31
Goal 2: Provide a portfolio of resources to educate and empower our members to thrive in the polymer enterprise. [Impact, H; Resources, H]
Strategy 1A: By Fall ACS meeting 2018, design a modern programming process that serves the entire POLY community. [Impact, M; Resources, M] Champion: Corinne L./Sarah M. | 2018-08-19 | Corinne Lipscomb | Brett or Thomas? | Corinne, Kathy, Thomas, Justin or Emily, Brett |  |  |  | unknown status
Task 1: Establish Team |  |  |  |  | TBD |  | 2018-03-19
Task 2: Develop SOP for Programming |  |  |  |  | TBD |  | 2018-05-31
Task 3: Propose system and cost estimate |  |  |  |  | TBD |  | 2019-01-31
Task 4: Implement SOP |  |  |  |  | TBD |  | 8/31/19??
Strategy 1B: By fall 2018 create a process to increase POLY participation in regional meetings. [Impact, M; Resources, M] Champion: Corinne L./Sarah M. | 2018-08-19 | Sarah Morgan | Dadmun? | Potential: Blum, Madsen, Savin, regional members, grad student members |  |  |  | unknown status
Task 1: Invite Mark Dadmun to serve as team lead |  |  |  |  | Sarah |  | 2018-02-28
Task 2: Create Team |  |  |  |  | Dadmin |  | 2018-08-19
Task 3: Contact ACS regional meetings coordinators; Engage symposium organizers; identify POLY members to organize at regional meetings |  |  |  |  | Team |  | 2019-08-31
Strategy 2: Appoint a webinar committee (by spring 2018 NOLA meeting) to define POLY’s webinar program. [Impact, H; Resources, L] Champion: Marc H. | 2018-03-16 | Marc Hillmyer | Marc? | Potential: Mike Meador, Sarah Morgan, Brent Sumerlin, Greg Tew, Andrea Kasko, Erik Berda, Kat Knauer, Joe Elabd, Toby Nelson, Josh Speros, Megan Robertson, Christine Luscombe |  |  |  | Carlee working with Marc to publicize and post videos to YouTube and add new memberships. Update Jan. 2019: Eric Amis has agreed to Chair the Webinar Committee for future planning
Task 1: Appoint Committee |  |  |  |  | Diana and Marc |  | 2018-03-16
Task 2: Line up speakers, coordinate with ACS/POLY |  |  |  |  | TBD Lead |  | 2/1/18, 5/1/18, 9/1/18
Strategy 3: Organize a virtual workshop/tutorial on a contemporary topic in the next 8 months; launch in Q1 2019. [Impact, H; Resources, H] Champion: Marc H./Toby N. | 2018-12-31 | Marc Hillmyer/Toby Nelson | TBD | TBD |  |  |  | Hillymer has submitted a web-shop proposal to be approved by exec. Dominik Konkolewicz (Miami U) to organize, 7K requested of POLY, topic: Controlled Polymerization, date est. June 2019
Task 1: Establish Team |  |  |  |  | Marc |  | 2018-07-01
Task 2: Contact ACS |  |  |  |  | Marc/Toby |  | 2018-02-28
Task 3: Recruit expertise team member |  |  |  |  | Team |  | 4/31/18
Task 4: Select contemporary topic |  |  |  |  | Team |  | 2018-08-19
Task 5: Contact potential speakers |  |  |  |  | Team |  | 2018-09-30
Task 6: Determine the Workshop cost |  |  |  |  | Team |  | 2018-09-30
Task 7: Determine the Workshop attendance fee |  |  |  |  | Team |  | 2018-09-30
Task 8: Host Workshop |  |  |  |  | Team |  | 2019-04-01
Goal 3: Effectively communicate the importance and activities of the polymer community to our members, polymer practitioners and the public at large. [Impact, H; Resources, M-H]
Strategy 1. By Q2, 2019, create, collect, and distribute relevant scientific content via social media outlets. [Impact, H; Resources, M] Champion: Johan F./Derek P. | 4/31/18 | Johan/Derek | TBD | Potential: Lesia, Emily Pentzer, Dan Savin, Justin Kennemur, Student Chapter Presidents/members |  |  |  | done - POLY Bus. Office works with Johan on "Researcher of the Month" on Facebook. Need Twitter posting.
Task 1: Establish Team/decide on outlets |  |  |  |  | Johan/Derek |  | 2018-03-19
Task 2: Highlights of Research |  |  |  |  | Derek |  | 2018-03-19 | 1st of month
Task 3: Highlights of Authors |  |  |  |  | Johan |  | 2018-03-19 | 15th of month
Task 4: News Aggregator |  |  |  |  | TBD |  | 2018-03-19 | TBD
Strategy 2: By Q3, 2019, create content for YouTube channel including, but not limited to, new member orientation video and meet a polymer scientist series. [Impact, H; Resources, M]. Champion: Justin K./Erik B. | 2018-09-30 | Berda and Kennemur | TBD | TBD |  |  |  | Carlee provided You Tube login info. Offered to assist with video uploads
Task 1: Team Composition and Lead |  |  |  |  | Berda and Kennemur |  | 2018-03-19
Task 2: Orientation Content |  |  |  |  | TBD |  | 2019-03-30 | should this be combined with Strat 1.1… POLY Bus. Office proposes a change in deadline to 12/31/2019
Task 3: Poly Scientist Vid |  |  |  |  | TBD |  | 2019-03-30
Task 4: Get speakers and make videos |  |  |  |  | TBD |  | 9/31/2019
Task 5: Launch content |  |  |  |  | TBD |  | 2018-12-31
Strategy 3: By Q2, 2019, Increase the number of e-news releases to one/month by expanding content to include more technical focus/information. [Impact, M; Resources, M] Champion: Mary Ann M./Karl H. | 2019-06-30 | Mary Ann Meador | TBD | Potential: Karl Haider, MaryAnn Meador, industry members, non-industry members |  |  |  | done - POLY Bus. Office is sending announcements by e-news bi-weekly; action plan in place. 11 announcements completed to date and plans are to continue
Task 1: Establish Team |  |  |  |  | Mary Ann |  | 2018-03-19
Task 2: Using existing poster awards at ACS Meetings, highlight poster awardees by linking posters in its own spotlight e-news |  |  |  |  | Semra Colak |  | 2018-03-19 | done - Semra Colak forwards pdf of posters to POLY Business Office
Task 3: Feature a member of the month/spotlight… Develop a questionnaire, identify a list of contributors, and implement |  |  |  |  | Haider/Meador |  | 2018-08-19 | done
Task 4: Identify the feasibility of linking to journals and post content. |  |  |  |  | Haider/Meador |  | 3/19/219 | to do… is there still interest?